## Sheet1
Work Breakdown Structure
Sr No | Work Item | Dependencies | Connect With | Work Allocated To | Target Date | Status
Pre-Req
1 | Git Repository |  |  | Suyash | 2023-06-30 | Closed
Implementation
1 | wire Frame |  |  | Omkar | 2023-06-30 | Closed
2 | Logo Design |  |  | Varun | 2023-06-30 | Closed
3 | Angular Project Creation |  |  | Suyash | 2023-06-30 | Closed
4 | DataBase Hosted on MsSql |  |  | Omkar | 2023-07-01 | Closed
5 | Scaffolding of DataBase |  |  | Varun | 2023-07-01 | Closed
6 | Api Creation - Territary Rest |  |  | Adinath | 2023-07-03 | Closed
7 | Api Creation - Employee Rest |  |  | Shivani | 2023-07-03 | Closed
8 | Api Creation - Login |  |  | Adinath | 2023-07-04 | Closed
9 | Api Creation - SignUp |  |  | Shivani | 2023-07-04 | Closed
10 | Api Creation - Shipper Rest |  |  | Shivani | 2023-07-05 | Closed
11 | Api Creation - Orders Rest |  |  | Adinath | 2023-07-05 | Closed
12 | UI Creation - Login |  |  | Ishant | 2023-07-05 | Closed
13 | UI Creation - SignUp(Admin) |  |  | Suyash | 2023-07-05 | Closed
14 | UI Creation - SignUp(Shipper) |  |  | Shivani | 2023-07-05 | Closed
15 | UI Creation - SignUp(Employee) |  |  | Suyash | 2023-07-05 | Closed
16 | UI Creation - Dashboard |  |  | Tanmay | 2023-07-06 | Closed
17 | UI & Integration with Api - Login |  |  | Adinath | 2023-07-06 | Closed
18 | UI & Integration with Api - SignUp(Admin) |  |  | Suyash | 2023-07-06 | Closed
19 | UI & Integration with Api - SignUp(Shipper) |  |  | Suyash | 2023-07-06 | Closed
20 | UI & Integration with Api - SignUp(Employee) |  |  | Tanmay | 2023-07-06 | Closed
21 | UI & Integration with Api - Admin Dashboard |  |  | Suyash | 2023-07-06 | Closed
22 | UI & Integration with Api - EmployeeDashboard |  |  | Suyash | 2023-07-06 | Closed
23 | UI & Integration with Api - Shipper Dashboard |  |  | Tanmay | 2023-07-07 | WIP
24 | UI & Integration with Api - Order Details Dashboard |  |  | Shivani | 2023-07-07 | WIP
Quality Assurance
1 | Api Testing - Employee |  |  | Adinath | 2023-07-03 | Closed
2 | Api Testing - Orders |  |  | Varun | 2023-07-03 | Closed
3 | Api Testing - Territary |  |  | Pallavi | 2023-07-03 | Closed
4 | Api Testing - Shipper |  |  | Shivani | 2023-07-03 | Closed
5 | Api Testing - Login |  |  | Suyash | 2023-07-04 | Closed
6 | Api Testing - SignUp |  |  | Tanmay | 2023-07-04 | Closed
7 | UI Testing - Login |  |  | Ishant | 2023-07-05 | Closed
8 | UI Testing - SignUP(Admin) |  |  | Omkar | 2023-07-05 | Closed
9 | UI Testing - SignUP(Shipper) |  |  | Varun | 2023-07-05 | Closed
10 | UI Testing - SignUP(Employee) |  |  | Pallavi | 2023-07-05 | Closed
11 | UI Testing - Admin Dashboard |  |  | Varun | 2023-07-06 | Closed
12 | UI Testing - Shipper Dashboard |  |  | Suyash | 2023-07-07 | Open
13 | UI Testing - Employee Dashboard |  |  | Ishant | 2023-07-07 | Open
14 | UI & Integration Testing -Login |  |  | Adinath | 2023-07-06 | Closed
15 | UI & Integration Testing -SignUp(Admin) |  |  | Ishant | 2023-07-06 | Closed
16 | UI & Integration Testing -SignUp(Shipper) |  |  | Varun | 2023-07-06 | Closed
17 | UI & Integration Testing -SignUp(Employee) |  |  | Omkar | 2023-07-06 | Closed
18 | UI & Integration Testing -Admin Dashboard |  |  | Pallavi | 2023-07-07 | Open
19 | UI & Integration Testing -Shipper Dashboard |  |  | Ishant | 2023-07-07 | Open
20 | UI & Integration Testing -Employee Dashboard |  |  | Varun | 2023-07-07 | Open
Release Setup
1 | Azure App Service Web API Application |  |  | Ishant | 2023-07-07 | WIP
2 | Azure App Service Angular Application |  |  | Tanmay | 2023-07-07 | WIP
3 | Azure Storage Account and Blob Storage |  |  | Omkar | 2023-07-07 | WIP
4 | Azure Logic App |  |  | Pallavi | 2023-07-07 | WIP
5 | Azure Function App |  |  | Varun | 2023-07-07 | WIP
Deployment
1 | Deployment Strategy |  |  |  | 2023-07-07 | Open
2 | Setup for deployment - APP |  |  |  | 2023-07-07 | Open
3 | Setup for deployment - API |  |  |  | 2023-07-07 | Open
4 | Setup - Dependendat Resources |  | DB, Logic app etc |  | 2023-07-07 | Open
5 | Test APP |  |  |  | 2023-07-07 | Open
6 | Test API |  |  |  | 2023-07-07 | Open
7 | Test Other Resources |  |  |  | 2023-07-07 | Open