## Sheet1
Work Breakdown Structure
Sr No | Work Item | Dependencies | Connect With | Work Allocated To | Target Date | Status
Pre-Req
1 | Git Repository |  |  | Suyash | 2023-06-30 | Closed
1 | Implementation
2 | Angular Project Creation |  |  | Suyash | 2023-06-30 | Closed
3 | HomePage |  |  | Tanmay | 2023-07-04 | WIP
4 | Release |  |  | Ishant | 2023-07-05 | WIP
5 | DataBase Hosted on MsSql |  |  | Omkar | 2023-07-01 | Closed
6 | Scaffolding of DataBase |  |  | Shivani | 2023-07-01 | Closed
7 | Shipper Rest Api |  |  | Shivani | 2023-07-01 | Closed
8 | Employee Rest Api |  |  | Shivani | 2023-07-03 | WIP
9 | Orders Rest Api |  |  | Adinath | 2023-07-03 | WIP
10 | Territary Rest Api |  |  | Adinath | 2023-07-01 | Closed
11 | Login Api |  |  | Suyash | 2023-07-01 | Closed
12 | SignUp |  |  | Suyash | 2023-07-01 | Closed
QA
1 | Login Module Testing |  |  | Suyash | 2023-07-03 | WIP
2 | SignUp Module Testing |  |  | Tanmay | 2023-07-03 | WIP
3 | Shipper Api Testing |  |  | Ishant | 2023-07-03 | WIP
4 | Employee Api Testing |  |  | Omkar | 2023-07-03 | WIP
5 | Orders Api Testing |  |  | Varun | 2023-07-03 | WIP
6 | Territary Api Testing |  |  | Pallavi | 2023-07-03 | WIP
Release Setup
1 | Azure App Service WebAPI Application |  |  | Ishant | 2023-07-05 | Opened
2 | Azure App Service Angular Application |  |  | Ishant | 2023-07-05 | Opened
3 | Azure Storage Account & Blob Storage |  |  | Varun | 2023-07-05 | Opened
4 | Azure Event Grid |  |  | Omkar | 2023-07-05 | Opened
Deployment