## Sheet1
Work Breakdown Structure
Sr No | Work Item | Dependencies | Connect With | Work Allocated To | Target Date | Status
Pre-Req
1 | Git Repository |  |  | Suyash | 2023-06-30 | Closed
Implementation
1 | Angular Project Creation |  |  | Suyash | 2023-06-30 | Closed
2 | DataBase Hosted on MsSql |  |  | Omkar | 2023-07-01 | Closed
3 | Scaffolding of DataBase |  |  | Varun | 2023-07-01 | Closed
4 | Territary Rest Api |  |  | Adinath | 2023-07-03 | Closed
5 | Employee Rest Api |  |  | Shivani | 2023-07-03 | Closed
6 | Shipper Rest Api |  |  | Shivani | 2023-07-05 | Closed
7 | Orders Rest Api |  |  | Adinath | 2023-07-05 | Closed
8 | Release |  |  | Ishant | 2023-07-05 | Closed
9 | HomePage |  |  | Tanmay | 2023-07-05 | Closed
10 | Login Api |  |  | Shivani | 2023-07-04 | Closed
11 | SignUp Api |  |  | Shivani | 2023-07-04 | Closed
12 | Dashboard(Shipper) |  |  | Suyash | 2023-07-06 | WIP
13 | Dashboard(Employee) |  |  | Suyash | 2023-07-06 | WIP
14 | Dashboard(Administrator) |  |  | Tanmay | 2023-07-06 | WIP
15 | Module 1 (Administrator Screen) - UI & Intgration |  |  | Tanmay | 2023-07-06 | WIP
16 | Module 2 (Employee Screen)- UI & Integration |  |  | Suyash | 2023-07-06 | WIP
17 | Module 3 - (Shipper Screeen)UI & Integration |  |  | Suyash | 2023-07-06 | WIP
18 | Module 4 (Email) - Intgration |  |  | Varun | 2023-07-06 | WIP
19 | Module 5 - UI and Integration |  |  | Tanmay | 2023-07-06 | WIP
QA
1 | Employee Api Testing |  |  | Adinath | 2023-07-03 | Closed
2 | Orders Api Testing |  |  | Varun | 2023-07-03 | Closed
3 | Territary Api Testing |  |  | Pallavi | 2023-07-03 | Closed
4 | Login Module Testing |  |  | Suyash | 2023-07-05 | Closed
5 | SignUp Module Testing |  |  | Tanmay | 2023-07-05 | Closed
6 | Shipper Api Testing |  |  | Shivani | 2023-07-05 | Closed
7 | Administrator Screen Testing |  |  | Varun | 2023-07-06 | WIP
8 | Shipper Screen Testing |  |  | Suyash | 2023-07-06 | WIP
9 | Employee Screen Testing |  |  | Ishant | 2023-07-06 | WIP
Release Setup
1 | Azure App Service Web API Application |  |  | Ishant | 2023-07-06 | Open
2 | Azure App Service Angular Application |  |  | Varun | 2023-07-06 | Open
3 | Azure Storage Account and Blob Storage |  |  | Omkar | 2023-07-06 | Open
4 | Azure Logic App |  |  | Ishant | 2023-07-06 | Open
5 | Azure Function App |  |  | Varun | 2023-07-06 | Open
Deployment
1 | Deployment Strategy |  |  |  | 2023-07-07 | Open
2 | Setup for deployment - APP |  |  |  | 2023-07-07 | Open
3 | Setup for deployment - API |  |  |  | 2023-07-07 | Open
4 | Setup - Dependendat Resources |  | DB, Logic app etc |  | 2023-07-07 | Open
5 | Test APP |  |  |  | 2023-07-07 | Open
6 | Test API |  |  |  | 2023-07-07 | Open
7 | Test Other Resources |  |  |  | 2023-07-07 | Open